This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Please enter your name as it appears in Canvas.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
## Product_Backlog
Project Name	Mavs Arboreta, Nursery, and Garden Association (MANGA)
Product Name:						Complete Fields in Green!!!
Team ID:						Product Backlog Burn Chart / Features Remaining at end of Sprint / Sprints

	Team Member Name					Initials	Student ID
Required	Bhuwan Shrestha					B S	1001808072

Sprint #	Remaining	Completed This Sprint				Comment
0	30				Total	Total number of features (in column H)
1	25	5			1	Total features left at the end of Sprint #1
2	20	5			2	Total features left at the end of Sprint #2
3	16	4			3	...and so on
4	14	2
5	12	2
6	10	2

©2016-2020 by George F. Rice
This work is licensed under a Creative Commons Attribution 4.0 International License.						Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
						Additional features may be proposed by the student but must be approved by the Product Owner in writing
						Features
Feature ID	Priority	Required	Bonus	Est	Planned	Status	As a...	I want to...	So that I can…	Notes
STORE	1	1		13	1	Finished in Sprint 1	Manager	Create an empty store (via CLI)	Open new branches and franchises	Need a Store class and a simple main()
TOOL	2	1		8	1	Finished in Sprint 1	Inventory	Add a Tool product to the store (via CLI)	Add new products to sell	Need a Product base class and trivial Tool derived class
LISTPROD	3	1		5	1	Finished in Sprint 1	Sales Staff	List all products in the store (via CLI)	Find products my customers need	Simple iteration loop
PLANT	4	1		5	1	Finished in Sprint 1	Inventory	Add a Plant product to the store (via CLI)	Add new products to sell	Simple derived class and additional menu item
MULCH	5	1		5	1	Finished in Sprint 1	Inventory	Add a Mulch product to the store (via CLI)	Add new products to sell	Simple derived class and additional menu item
WINDOW	6	2		13	2	Finished in Sprint 2	Manager	Create a main window for the store	Use the software more easily	Recommend baselining Nim from Lecture 13
TOOLW	7	2		8	2	Finished in Sprint 2	Inventory	Add New Tool series of dialogs to add Tool product	More easily create new Tools	Recommend baselining EntryDialog from Lecture 14
LISTW	8	2		5	2	Finished in Sprint 2	Sales Staff	List all products in the main window data area	Find products my customers need	Try using std::ostringstream to capture operator<< formatting
PLANTW	9	2		3	2	Finished in Sprint 2	Inventory	Add New Plant dialogs	More easily create new Plants
MULCHW	10			3	2	Finished in Sprint 2	Inventory	Add New Mulch dialogs	More easily create new Mulch products
SAVE	11	3		13	3	Finished in Sprint 3	Manager	Save all products to untitled.manga	Avoid rekeying all data (!)	This requires modifying the “model” to save and reload each object from a provided stream
LOAD	12	3		8	3	Finished in Sprint 3	Manager	Load saved products from a selected filename	Avoid rekeying all data (!)	Use Gtk::FileChooser
SAVEAS	13	3		8	3	Finished in Sprint 3	Manager	Save as a specified / selected filename	Manage multiple stores	Use Gtk::FileChooser
ABOUT	14	3		1	3	Finished in Sprint 3	Manager	Provide About dialog for documenting licenses	Avoid a lawsuit	Use Gtk::AboutDialog
CUSTOMER	15	4		21	4	Finished in Sprint 4	Sales Staff	Create a new Customer via a unified dialog	Add a new customer	Will need a Customer class, a Store::_customers vector, and a dialog to create them
LISTCUST	16	4		8	4	Finished in Sprint 4	Sales Staff	List all Customers in the main window data area	Find the current customer	Will need appropriate add and iterate methods for Store
STATUS	17	5			5	Finished in Sprint 5	Manager	Add a status bar	Monitor program operation more clearly	Recommend a Gtk::Label and Mainwin methods to update and clear the status bar. Consider using Pango for more attractive status!
ORDER	18	5		21	5	Finished in Sprint 5	Sales Staff	Create an Order	Sell stuff!	Will need an Order class, Store::_orders vector, and dialog to create them
LISTORD	19	5		5	5	Finished in Sprint 5	Sales Staff	List all Orders (with cost) in the main data area	Find the order for a Customer
TOOLBAR	20	5		8	5	Finished in Sprint 5	Sales Staff	Add a tool bar	Access program functions more easily	Include a functionality from main menu except exit and help
SORTCUST	21	6		8	6	Finished in Sprint 6		Sort the Customer list by name
ITERATORS	22	6		13	6	Finished in Sprint 6		REFACTOR: Use iterators with Store's vectors
						BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!
UNIFIED	23		25	13	6	Finished in Sprint 6	Sales Staff	Replace all remaining dialog sequences with unified dialogs each	Enter data more quickly
SCROLL	24		10	5			Customer	Make the main window’s data area scrollable	See large volumes of data	The exact settings (e.g., are the scrollbars always visible or only when scrolling is available?) are up to you
DEPRECATE	25		25	13			Inventory	Deprecate a product	Avoid selling products that are out of production	This requires a Boolean with getter and setter in the Options and Desktop classes to indicate which are deprecated. The index number may pose interesting challenges, since deprecation will create gaps.
STATUS++	26		15	8	6		Manager	Replace the Gtk::Label for the status bar with Gtk::Statusbar, and maintain a message stack	Better track status of messages	Just swapping Gtk::Statusbar for Gtk::Label is trivial. Think through how to manage a first-in last-out stack of messages
RMPROD	27		25	13			Sales Staff	Remove a product from an order in progress	More quickly assist indecisive Customers
STATE	28		40	21			Manager	Track order state: pending, paid, complete	Collect metrics on order processing
EDITCUST	29		15	8	6	Finished in Sprint 6	Sales Staff	Enable editing any Customer attribute(s)	Keep our CRM data up to date
EDITPROD	30		25	13			Inventory	Enable editing a Product's name, price, and description	More quickly track changes to our portfolio of products

## Sprint_01_Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 06		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 13		Sprint Burn Chart / Tasks / Days
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	17
Day 1 Left	12	5
Day 2 Left	8	4
Day 3 Left	7	1
Day 4 Left	7	0
Day 5 Left	4	3
Day 6 Left	4	0
Day 7 Left	0	4
			Note: Due to the late project start, the results of this sprint will be provided to you (although you may use your own solution if you prefer)
Task ID	Feature ID	Assigned To	Task	Status	Notes
1	TOOL		Write the Product class	Completed Day 1	Test each class and method as it is written
2	TOOL		Write operator<< for Product	Completed Day 1	Commit and push AT LEAST once every class or update
3	TOOL		Write Store::add_product, products, and product(int)	Completed Day 1
4	TOOL		Write the Options class sans to_string	Completed Day 1
5	TOOL		Write the Tool class	Completed Day 1
6	STORE		Write Store class	Completed Day 2
7	STORE		Write operator<< for Store	Completed Day 2
8	STORE		Write first draft of main() function – add Tools	Completed Day 2
9	LISTPROD		Update main() function to list Products (polymorphism should enable other products to list as well)	Completed Day 2
10	PLANT		Write Exposure enum class	Completed Day 3
11	PLANT		Write Exposure operator<< function	Completed Day 5
12	PLANT		Write Plant class	Completed Day 5
13	PLANT		Update main() function to create Plant products	Completed Day 5
14	MULCH		Write Material enum class	Completed Day 7
15	MULCH		Write Material operator<< function	Completed Day 7
16	MULCH		Write Mulch class	Completed Day 7
17	MULCH		Update main() function to create Mulch products	Completed Day 7
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint_02_Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Oct 13		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 20		Sprint Burn Chart / Tasks / Days
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	14
Day 1 Left	11	3
Day 2 Left	10	1
Day 3 Left	5	5
Day 4 Left	2	3
Day 5 Left	0	2
Day 6 Left	0	0
Day 7 Left	0	0
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1	WINDOW	B S	Created GUI Mainwin using gtkmm library	Completed Day 1
2	WINDOW	B S	Added menubar with file menu, insert menu and view menu	Completed Day 1
3	WINDOW	B S	Added functions when clicked on menuitem	Completed Day 1
4	WINDOW	B S	Added windows for inserting parameters for products according to their types i.e. tools, plants or mulchs.	Completed Day 2
5	TOOLW	B S	Added ComboTextBox to input name, price and description	Completed Day 3
6	TOOLW	B S	Added Submit and Cancel Button	Completed Day 3
7	PLANTW	B S	Added ComboTextBox to input name, price, description and species	Completed Day 3
8	PLANTW	B S	Added Dropdown Button to select the exposure type of the plant	Completed Day 3
9	PLANTW	B S	Added Submit and Cancel Button	Completed Day 3
10	MULCHW	B S	Added ComboTextBox to input name, price, description and species	Completed Day 4
11	MULCHW	B S	Added Dropdown Button to select the material type of the mulch	Completed Day 4
12	MULCHW	B S	Added Submit and Cancel Button	Completed Day 4
13	LISTW	B S	Added products menuitem in view menu	Completed Day 5
14	LISTW	B S	Set display label by iterating throught the list of products to show the products in the main window.	Completed Day 5
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint_03_Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Oct 20		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 27		Sprint Burn Chart / Tasks / Days
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	7
Day 1 Left	5	2
Day 2 Left	3	2
Day 3 Left	2	1
Day 4 Left	0	2
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1	SAVE	B S	When app runs for the firs time we five the default name to the filename attributes.	Completed Day 1
2	SAVE	B S	Called save functions from the store and saved in the default filename.	Completed Day 1
3	SAVE	B S	Saved Products according to their type in the created file using ostream	Completed Day 2
4	LOAD	B S	Load saved file from the directory by using istream.	Completed Day 2
5	SAVEAS	B S	When clicked in save as menu item it will popup the window where file can be saved in user defined filename.	Completed Day 3
6	ABOUT	B S	Added Help Menu in Menubar	Completed Day 4
7	ABOUT	B S	Added About menu item which would open the dialog showing app logo and description about the app with the contributers name.	Completed Day 4
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint_04_Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Oct 27		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 03		Sprint Burn Chart / Tasks / Days
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	7
Day 1 Left	5	2
Day 2 Left	3	2
Day 3 Left	2	1
Day 4 Left	1	1
Day 5 Left	0	1
Day 6 Left	0	0
Day 7 Left	0	0
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1	CUSTOMER	B S	Created class for customer with attributes name, phone and email.	Completed Day 1
2	CUSTOMER	B S	Created Constructor and methods to save, load and print the customers.	Completed Day 1
3	CUSTOMER	B S	Added new menu item to add customer in the store.	Completed Day 2
4	CUSTOMER	B S	Made a dialog with three Entry for name, phone and email.	Completed Day 2
5	CUSTOMER	B S	Made save and cancel button with functioning	Completed Day 3
6	LISTCUST	B S	Made customers menu item in views menu	Completed Day 4
7	LISTCUST	B S	Made a functioning of view cumstomers button by setting display label by using loop through all the customers in the vectors.	Completed Day 5
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint_05_Backlog
Sprint #	5		Complete Fields in Green!!!
Start on	Nov 03		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 10		Sprint Burn Chart / Tasks / Days
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	14
Day 1 Left	10	4
Day 2 Left	8	2
Day 3 Left	6	2
Day 4 Left	5	1
Day 5 Left	3	2
Day 6 Left	1	2
Day 7 Left	0	1
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1	STATUS	B S	Added status label in the Mainwin class.	Completed Day 1
2	STATUS	B S	Made a method to set the text in the label attributes.	Completed Day 1
3	STATUS	B S	Added status in the Vbox using pack_shrink.	Completed Day 1
4	STATUS	B S	Updated status each time whenever something is being changed and updated in the program to show the status in the bottom of the window.	Completed Day 1
5	ORDER	B S	Created Item class with attributes quantity and the product.	Completed Day 2
6	ORDER	B S	Created all the methods to save, load, calculating subtotal and print the item.	Completed Day 2
7	ORDER	B S	Created new order class with attributes of customer and vector of items.	Completed Day 3
8	ORDER	B S	Created all the methods to save, load, add the items and calculating total.	Completed Day 3
9	ORDER	B S	Added menu item for order in the insert menu.	Completed Day 4
10	ORDER	B S	Made first dialog to choose the customer for which the order is being made by using a dialog with dropdown.	Completed Day 5
11	ORDER	B S	Made a Dialog window to add the quantity using spinbutton and products using the dropdown for the choosen customers from the first dialog.	Completed Day 5
12	LISTORD	B S	Made a orders menu item in the views menu.	Completed Day 6
13	LISTORD	B S	Set the display message by iterating throught the vector of all the orders made.	Completed Day 6
14	TOOLBAR	B S	Added toolbar with different toolbuttons to make new store file, open store file, save file, adding customers, orders, and showing customers, products and orders in the store as well.	Completed Day 7
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint_06_Backlog
Sprint #	6		Complete Fields in Green!!!
Start on	Nov 10		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 17		Sprint Burn Chart / Tasks / Days
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	11
Day 1 Left	8	3
Day 2 Left	6	2
Day 3 Left	2	4
Day 4 Left	2	0
Day 5 Left	2	0
Day 6 Left	1	1
Day 7 Left	0	1
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1	SORTCUST	B S	Made a new method in the store class for sorting of the customers according to their name in alphabetical order.	Completed Day 1
2	SORTCUST	B S	Called the method in the constructor of the store to make the sorting of the customers by default in alphabetical order.	Completed Day 1
3	SORTCUST	B S	Clicked on view customers to display the sorted customers in the window.	Completed Day 1
4	UNIFIED	B S	Created a single window while adding tools, plant and mulch instead of promptiong different windows.	Completed Day 2
5	UNIFIED	B S	Added Entry for the text values and dropdown for the fixed items wihile adding the products.	Completed Day 2
6	EDITCUST	B S	Added edit customer method in the store class by using the index of the respective customer in the vector.	Completed Day 3
7	EDITCUST	B S	Added Edit menu in the menubar and edit customer menu item in the edit menu.	Completed Day 3
8	EDITCUST	B S	Made a first dialog to choose the customer from the dropdown.	Completed Day 3
9	EDITCUST	B S	The index position of the cusomer was taken to the second dialog where new insformation was input to update the selected customer.	Completed Day 3
10	ITERATORS	B S	Order list was printed using the iterators on view orders click functions in mainwin.	Completed Day 6
11	SCROLL	B S	Scroll bar was added in the main window to display the list of customers, products and the orders. If the list was long it can be scrolled vertically	Completed Day 7
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84